## Defect Log
Project Code: | CMS Click and Change |  | This template is created for group only, please do not use for any other purposes.
Created Date | Title | Description | Status | QC Activity | Defect Origin | Priority | Product Type | Severity | Product | Type | Detected By | Assigned To | Deadline | Corrective Action | Cause Analysis | Reason | Fixed Date | Closed Date | Warning: This session is created only for doing value validation. Please do not do modify this.
2011-10-21 | Media Option_Permission | Phân quyền Media cho user, dư thừa không cần thiết. | Error
2011-10-21 | Media Option_Component | Cấu hình media, dư thừa không cần thiết. | Error | [15 empty] | Member List | Status | QC Activity | Defect Origin | Priority | Product Type | Severity | Type | Status | Reason
2011-10-21 | Category và section | Lỗi giá trị không đồng nhất (giá trị liên kết giữa 2 bảng) | Error | [16 empty] | Accepted | Acceptance test | Coding | Immediately | Achitectural design | Fatal | Bussiness logic | Error | Change requirement
2011-10-21 | Article | Thiếu catid | Error | [16 empty] | Approved | After release review | Configuration Manament | High | CM Plan | Serious | Coding logic | Assigned | Duplicated
2011-10-21 | Event trong Article | Thiếu event select change của combox section | Error | [16 empty] | Assigned | After release test | Customer support | Normal | Coding convention | Medium | Coding standard | Fixing | No need to change
2011-10-21 | Media Manager | chkThumbnailView và chkDetailView không thể dùng checkbox | Error | [16 empty] | Cancelled | Audit | Deployment | Low | Customer saticfaction survey | Cosmetic | Data, Database integrity | Corrected | Other
2011-10-21 | Media Manager | txtFilePath bị dư | Error | [16 empty] | Closed | Code review | Design |  | Database |  | Design issue | Dilivered | Unable to fix
2011-10-21 | Media Manager | chkSelectFile không cần thiết | Error | [16 empty] | Cofirmed | Document review | Project Manament |  | Deployment package |  | Document | Validated | Unable to change
2011-10-21 | Media Manager | Thiếu sự kiện select chọn trong folder | Error | [16 empty] | Corrected | Final Inspection | Quality control |  | Design prototype |  | Feature missing | Approved | Mistake of developer
[20 empty] | Delivered | Intergration test | Requirement |  | Detailed design |  | Other | Closed
[20 empty] | Error | Other Inspection | Test |  | Installation manual |  | Performance | Cofirmed
[20 empty] | Fixing | Other review |  |  | Meeting minute |  | Portablity | Cancelled
[20 empty] | Validated | Other test |  |  | Other |  | Security, Access control | Accepted
[21 empty] | Quality Inspection |  |  | Plan |  | Tools
[21 empty] | Regression test |  |  | Release note |  | User interface
[21 empty] | System test |  |  | Software module
[21 empty] | Unit test |  |  | System test case
System test plan
Test case
Test data
Test plan
Test report