## Defect Log
c
Project Code: | CMS Click and Change
Created Date (*) | Title (*) | Description (*) | Status (*) | QC Activity | Defect Origin | Priority (*) | Product Type (*) | Severity (*) | Product (*) | Type | Detected By (*) | Assigned To (*) | Deadline (*) | Corrective Action (*) | Cause Analysis | Fixed by | Fixed Date (*) | Closed Date (*) | Warning: This session is created only for doing value validation. Please do not do modify this.
2011-10-21 | Media Option_Permission | Phân quyền Media cho user, dư thừa không cần thiết. | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_MediaManager.xls, revesion 128 | Design issue | TuTM | BaoNDD | 2011-10-22 | Phần này không cần làm | Không cần quá chi tiết như vậy |  | 2011-10-22 | 2011-10-22
2011-10-21 | Media Option_Component | Cấu hình media, dư thừa không cần thiết. | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_MediaManager.xls, revesion 128 | Design issue | TuTM | BaoNDD | 2011-10-22 | Phần này không cần làm | Không cần quá chi tiết như vậy |  | 2011-10-22 | 2011-10-22 | Member List | Status | QC Activity | Defect Origin | Priority | Product Type | Severity | Type | Status | Reason
2011-10-21 | Category và section | Lỗi giá trị không đồng nhất (giá trị liên kết giữa 2 bảng) | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_ContentManager_New&Edit.xls, revesion 128 | Design issue | BaoNDD | TuTM | 2011-10-22 | Sửa lại giá trị tương ứng cho đồng nhất | Sai sót của developer |  | 2011-10-22 | 2011-10-22 |  | Accepted | Acceptance test | Coding | Immediately | Achitectural design | Fatal | Bussiness logic | Error | Change requirement
2011-10-21 | Article | Thiếu catid | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_ContentManager_New&Edit.xls, revesion 128 | Design issue | BaoNDD | TuTM | 2011-10-22 | Thêm catid | Sai sót của developer |  | 2011-10-22 | 2011-10-22 |  | Approved | After release review | Configuration Manament | High | CM Plan | Serious | Coding logic | Assigned | Duplicated
2011-10-21 | Event trong Article | Thiếu event select change của combox section | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_ContentManager_New&Edit.xls, revesion 128 | Design issue | TuanVA | TuTM | 2011-10-22 | Thêm event select change của combox section | Sai sót của developer |  | 2011-10-22 | 2011-10-22 |  | Assigned | After release test | Customer support | Normal | Coding convention | Medium | Coding standard | Fixing | No need to change
2011-10-21 | Media Manager | chkThumbnailView và chkDetailView không thể dùng checkbox | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_MediaManager.xls, revesion 128 | Design issue | TuTM | TuanVA | 2011-10-22 | Dùng button hoặc dùng link | Sai sót của developer |  | 2011-10-22 | 2011-10-22 |  | Cancelled | Audit | Deployment | Low | Customer saticfaction survey | Cosmetic | Data, Database integrity | Corrected | Other
2011-10-21 | Media Manager | txtFilePath bị dư | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_MediaManager.xls, revesion 128 | Design issue | TuanVA | TuanVA | 2011-10-22 | Bỏ giá trị này | Sai sót của developer |  | 2011-10-22 | 2011-10-22 |  | Closed | Code review | Design |  | Database |  | Design issue | Dilivered | Unable to fix
2011-10-21 | Media Manager | chkSelectFile không cần thiết | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_MediaManager.xls, revesion 128 | Design issue | TuanVA | TuanVA | 2011-10-22 | Bỏ giá trị này | Sai sót của developer |  | 2011-10-22 | 2011-10-22 |  | Cofirmed | Document review | Project Manament |  | Deployment package |  | Document | Validated | Unable to change
2011-10-21 | Media Manager | Thiếu sự kiện select chọn trong folder | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_MediaManager.xls, revesion 128 | Design issue | BaoNDD | TuanVA | 2011-10-22 | Thêm event select chọn trong folder | Sai sót của developer |  | 2011-10-22 | 2011-10-22 |  | Corrected | Final Inspection | Quality control |  | Design prototype |  | Feature missing | Approved | Mistake of developer
[20 empty] | Delivered | Intergration test | Requirement |  | Detailed design |  | Other | Closed
2011-10-21 | Language manager | Dư column Version | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_Language manager.xlsx, revesion 126 | Design issue | HuyDV | LinhTA |  | Bỏ Column Version ( sửa lại các phần : giao diện, definition items, mapping item to db, events có liên quan tới phần bị bỏ này). | Rặp khuôn theo Joomla | Other | 2011-10-22 | 2011-10-22 |  | Error | Other Inspection | Test |  | Installation manual |  | Performance | Cofirmed
2011-10-21 | Language manager | Dư column Date | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_Language manager.xlsx, revesion 126 | Design issue | ThanhChV | LinhTA |  | Bỏ Column Date( sửa lại các phần : giao diện, definition items, mapping item to db, events có liên quan tới phần bị bỏ này). | Rặp khuôn theo Joomla | Other | 2011-10-22 | 2011-10-22 |  | Fixing | Other review |  |  | Meeting minute |  | Portablity | Cancelled
2011-10-21 | New & Edit user | Dư phần Basic Setting | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_New&EditUser.xls, revesion 126 | Design issue | HuyDV | ThanhChV |  | Bỏ phần Basic setting(( sửa lại các phần : giao diện, definition items, mapping item to db, events có liên quan tới phần bị bỏ này). | Rặp khuôn theo Joomla | Other | 2011-10-22 | 2011-10-22 |  | Validated | Other test |  |  | Other |  | Security, Access control | Accepted
2011-10-21 | New & Edit user | Dư các group user : publisher, editor, super administrator, author, editor. | Corrected | Document review | Design | High | Detailed design | Serious | SDD_New&EditUser.xls,revesion 126 | Design issue | ThanhChV | ThanhChV |  | Bỏ các group user bị dư. | Rặp khuôn theo Joomla | Other | 2011-10-22 | 2011-10-22 |  |  | Quality Inspection |  |  | Plan |  | Tools
2011-10-21 | New & Edit user(mapping items to db) | Dư column Cofirm password trong phần mapping to db | Corrected | Document review | Design | Normal | Detailed design | Serious | SDD_New&EditUser.xls,revesion 126 | Design issue | LinhTA | ThanhChV |  | Bỏ column " cofirm password " trong thiết kế db User. | Sai sót của developer | Mistake of developer | 2011-10-22 | 2011-10-22 |  |  | Regression test |  |  | Release note |  | User interface
2011-10-21 | new & edit user | Dùng các radion button thay cho cac check box trong Assigned User Groups | Corrected | Document review | Design | High | Detailed design | Serious | SDD_New&EditUser.xls,revesion 126 | Design issue | LinhTA | ThanhChV |  | Thay các check box trong Assigned User Groups bằng radion button (( sửa lại các phần : giao diện, definition items, mapping item to db, events có liên quan tới phần bi sửa này). | Rặp khuôn theo Joomla | Other | 2011-10-22 | 2011-10-22 |  |  | System test |  |  | Software module
2011-10-21 | Contend manager _ Article manager(Item Definition) | mô tả thiếu item btnhelp trong phần item definiton | Corrected | Document review | Design | Low | Detailed design | Medium | SDD_ContentManager_DucNH.xls,revesion 126 | Design issue | LinhTA | DucNH |  | Bổ sung mô tả btnhelp vào phần definition item. | Sai sót của developer | Mistake of developer | 2011-10-22 | 2011-10-22 |  |  | Unit test |  |  | System test case
2011-10-21 | Contend manager_ Article manager(events) | Mô tả sai event của btnpublishArticle | Corrected | Document review | Design | High | Detailed design | Serious | SDD_ContentManager_DucNH.xls,revesion 126 | Design issue | ThanhChV | DucNH |  | Sửa lại event của btnpublishArticle | Sai sót của developer | Mistake of developer | 2011-10-22 | 2011-10-22 | [5 empty] | System test plan
2011-10-21 | Contend manager_ Article manager(events) | Mô tả sai event của btnunpublishArticle | Corrected | Document review | Design | High | Detailed design | Serious | SDD_ContentManager_DucNH.xls,revesion 126 | Design issue | LinhTA | DucNH |  | Sửa lại event của btnunpublishArticle | sai sót của developer | Mistake of developer | 2011-10-22 | 2011-10-22 | [5 empty] | Test case
2011-10-21 | Contend manager_ Article manager(item definition) | các items : pageNumberList, itemNotes có type là : html, mô tả type của item chưa rõ.! | Corrected | Document review | Design | Low | Detailed design | Cosmetic | SDD_ContentManager_DucNH.xls,revesion 126 | Design issue | LinhTA | DucNH |  | mô tả ( giải thích rõ hơn ) type của các items : pageNumberList, itemNotes . | sai sót của developer | Mistake of developer | 2011-10-22 | 2011-10-22 | [5 empty] | Test data
2011-10-21 | Contend manager_ Article manager(event) | các items : pageNumberList, itemNotes có type là : html, mô tả type của item chưa rõ.! | Corrected | Document review | Design | Low | Detailed design | Medium | SDD_ContentManager_DucNH.xls,revesion 126 | Design issue | ThanhChV | DucNH |  | mô tả lại event của btnreset. | sai sót của developer | Mistake of developer | 2011-10-22 | 2011-10-22 | [5 empty] | Test plan
2011-10-21 | New & Edit user | Nên gộp phần Name và Login nam lại làm một. | Corrected | Document review | Design | Normal | Detailed design | Medium | SDD_New&EditUser.xls, revesion 126 | Design issue | ThanhChV | ThanhChV |  | Bỏ text box name, sửa textbox login nam thành username ( sửa lại các phần : giao diện, definition items, mapping item to db, events có liên quan tới phần bị bỏ và bị sửa này). | Rặp khuôn theo Joomla | Other | 2011-10-22 | 2011-10-22 |  | Validated | Other test |  |  | Other |  | Security, Access control | Accepted
2011-10-21 | MenuManager | MenuManager_Copy/Mapping Item to database: thiếu Type | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Type Column |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | MenuManager_Copy/tbxTitile: thiếu format, thiếu lenght | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | MenuManager_Copy/tbxModuleName: thiếu format, thiếu lenght | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | MenuManager_Edit/Mapping Item to database: thiếu Type | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Type Column |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | MenuManager_Edit/tbxUniqueName: thiếu format, thiếu lenght | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | MenuManager_Edit/tbxDescription: thiếu format, thiếu lenght | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | MenuManager_Edit/tbxTitle: thiếu format, thiếu lenght | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | MenuManager_New/Mapping Item to database: thiếu Type | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Type Column |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | MenuManager_New/tbxUniqueName: thiếu format, thiếu lenght | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | MenuManager_New/tbxTitle: thiếu format, thiếu lenght | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | MenuManager_New/tbxDescription: thiếu format, thiếu lenght | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | MenuManager_New/tbxModuleName: thiếu format, thiếu lenght | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | CreatedMenu_Edit/Mapping Item to database: thiếu Type | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Type Column |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | CreatedMenu_Edit/tbxTitle: thiếu format, thiếu lenght | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | CreatedMenu_Edit/tbxLink: thiếu format, thiếu lenght, error check | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | CreatedMenus_New_NewMenuItem/Mapping Item to database: thiếu Type | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Type Column |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | CreatedMenus_New_NewMenuItem/tbxTitle: thiếu format, thiếu lenght | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | CreatedMenus_New_NewMenuItem/tbxAlias: thiếu format, thiếu lenght | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | CreatedMenus_New_NewMenuItem/tbxLink: thiếu format, thiếu length | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm Format, Length value |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | Content/Menu Manager: chưa có link | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm link to Menu Manager |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | Content/Menu Trash: chưa có link | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm link to Menu Trash |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | Content: thiếu MenuManager_Copy link | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm link to MenuManager_Copy link |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | Content: thiếu MenuManager_New link | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm link to enuManager_New link |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | Content: thiếu MenuManager_Edit link | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm link to MenuManager_Edit link |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | Content: thiếu MenuTrash link | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm link to MenuTrash link |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | Content : thiếu CreatedMenu_Copy link | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm link to CreatedMenu_Copy link |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | Content : thiếu CreatedMenus link | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm link to CreatedMenus link |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | Content : thiếu CreatedMenu_Move link | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm link to CreatedMenu_Move link |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | Content : thiếu CreatedMenus_New_NewMenuItem link | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm link to CreatedMenus_New_NewMenuItem link |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | MenuManager | Content : thiếu CreatedMenu_New_SeclectType link | Corrected | Document review | Design | Low | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThaoNX | ThiVT |  | Thêm link to CreatedMenu_New_SeclectType |  | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | User Manage | thiếu RECORD OF CHANGES | Error | Document review | Design | Normal | Detailed design |  | SDD_UserManager.xls, revision 120 | Design issue | ThaoNX | KhoaVT |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | User Manager | database: Chưa map item colName tới CSDL người dùng | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThiVT | KhoaVT |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | User Manager | database: Chưa map item colUserName tới CSDL người dùng | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThiVT | KhoaVT |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | User Manager | database: Chưa map item colLoggedIn tới CSDL người dùng | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThiVT | KhoaVT |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | User Manager | database: Chưa map item colEnable tới CSDL người dùng | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThiVT | KhoaVT |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | User Manager | database: Chưa map item colGroup tới CSDL người dùng | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThiVT | KhoaVT |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | User Manager | database: Chưa map item colEmail tới CSDL người dùng | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThiVT | KhoaVT |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | User Manager | database: Chưa map item colLastVisted tới CSDL người dùng | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThiVT | KhoaVT |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | User Manager | database: Item cboSelectGroup không cần map tới CSDL | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThiVT | KhoaVT |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | User Manager | database: Item cbocboSelectLogStatus không cần map tới CSDL | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | ThiVT | KhoaVT |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | Configuration Global | Item ttdFtpPassword: Thiếu error check các ký tự đặc biệt trong mật khẩu | Corrected | Document review | Design | Low | Detailed design |  | SDD_GlobalConfiguration.xlsx | Design issue | ThiVT | ThaoNX |  |  | Sai sót của developer | Mistake of developer | 2011-10-27 | 2011-10-27
2011-10-21 | Section Manager | database: Item GirdView không cần map tới CSDL vì đã map từng trường | Error | Document review | Design | Normal | Detailed design |  | SDD_ContentManager_DungDV.xlsx | Design issue | ThiVT | DungDV |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | Section Manager | database: Item colCatagory không map tới bảng Section mà lấy từ bảng Section_Catagory | Error | Document review | Design | Normal | Detailed design |  | SDD_ContentManager_DungDV.xlsx | Design issue | ThiVT | DungDV |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | Catagory Manager | database: Item GirdView không cần map tới CSDL vì đã map từng trường | Error | Document review | Design | Normal | Detailed design |  | SDD_ContentManager_DungDV.xlsx | Design issue | ThiVT | DungDV |  |  | Sai sót của developer | Mistake of developer
2011-10-21 | Font Page Manager | database: Item GirdView không cần map tới CSDL vì đã map từng trường | Error | Document review | Design | Normal | Detailed design |  | SDD_ContentManager_DungDV.xlsx | Design issue | ThiVT | DungDV |  |  | Sai sót của developer | Mistake of developer
22/10/2011 | Section Manager | database: các item trong phần này đều dư | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | KhoaVT | DungDV |  |  | Sai sót của developer | Mistake of developer | 22/10/2011
22/10/2011 | Category Manager | database: các item trong phần này đều dư | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | KhoaVT | DungDV |  |  | Sai sót của developer | Mistake of developer | 22/10/2011
22/10/2011 | Front Page Manager | database: các item trong phần này đều dư | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | KhoaVT | DungDV |  |  | Sai sót của developer | Mistake of developer | 22/10/2011
22/10/2011 | MenuManager | Sheet Contents - Menu Manager: chưa có link | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | KhoaVT | ThiVT |  |  | Sai sót của developer | Mistake of developer | 22/10/2011
22/10/2011 | MenuManager | Sheet Contents - Menu Trash: chưa có link | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | KhoaVT | ThiVT |  |  | Sai sót của developer | Mistake of developer | 22/10/2011
22/10/2011 | MenuManager | Mapping Item to database : hình như không có thao tác cho phần này | Error | Document review | Design | Normal | Detailed design |  | SDD_MenuManager.xls, revision 116 | Design issue | KhoaVT | ThiVT |  |  | Sai sót của developer | Mistake of developer | 22/10/2011
Note on B4: Created Date: Ngày viết Log
Note on C4: Title: Tên Log
Note on D4: Description: Mô tả Log.
Note on E4: Status: Tình trạng của Log
Note on F4: QC Activity: Người viết Log phát hiện bug nhờ hành động nào.
Note on G4: Defect Origin: Bug xảy ra do bước nào trong quy trình phát triển
Note on H4: Priority: Tính cấp thiết của Bug (có phải sửa ngay hay không)
Note on I4: Product Type: Loại sản phẩm chứa Bug.
Note on J4: Serverity: Mức độ nghiêm trọng của Bug
Note on K4: Product: Sản phẩm chứa Bug. Lưu ý: ghi rõ file nào chứa bug, ở revision nào.
Note on L4: Type: Phân loại bug.
Note on M4: Detected By: Người phát hiện hoặc người viết Log.
Note on N4: Assigned To: Người được giao việc sửa lỗi.
Note on O4: DeadLine: Hạn chót phải sửa xong.
Note on P4: Corrective Action: Phải sửa lỗi như thế nào. Nếu có thể xảy ra những lỗi tương tự ở các file khác thì đề nghị sửa luôn ở đây.
Note on Q4: Cause Analysis: Nguyên nhân gây ra lỗi.
Note on R4: Reason: Loại nguyên nhân gây ra lỗi.
Note on S4: Fixed Date: Ngày sửa xong.
Note on T4: Closed Date: Ngày đóng Bug.

## Design Form
Project Code:
Created Date | Title | Description | Status | QC Activity | Defect Origin | Priority | Product Type | Severity | Product | Type | Detected By | Assigned To | Deadline | Corrective Action | Cause Analysis | Fixed By | Fixed Date | Closed Date | Warning: This session is created only for doing value validation. Please do not do modify this.
2011-11-04 | login | user name: không được nhập ký tự ("#$%^&*@") | Error | Code review | Design | High | Coding convention |  | admin\forms\login.php revesion 231 |  | ThaoNX | LinhTA |  |  |  | TuTM | 2011-11-04
| Section New | Title: test joomla thấy nhập gì cũng được hic | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [6 empty] | Member List | Status | QC Activity | Defect Origin | Priority | Product Type | Severity | Type | Status | Reason
| Section New | Alias: | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [7 empty] | Accepted | Acceptance test | Coding | Immediately | Achitectural design | Fatal | Bussiness logic | Error | Change requirement
| Section Edit | Title | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [7 empty] | Approved | After release review | Configuration Manament | High | CM Plan | Serious | Coding logic | Assigned | Duplicated
| Section Edit | Alias | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [7 empty] | Assigned | After release test | Customer support | Normal | Coding convention | Medium | Coding standard | Fixing | No need to change
| Category New | Title | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [7 empty] | Cancelled | Audit | Deployment | Low | Customer saticfaction survey | Cosmetic | Data, Database integrity | Corrected | Other
| Category New | Alias | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [7 empty] | Closed | Code review | Design |  | Database |  | Design issue | Dilivered | Unable to fix
| Category Edit | Title | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [7 empty] | Cofirmed | Document review | Project Manament |  | Deployment package |  | Document | Validated | Unable to change
| Category Edit | Alias | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [7 empty] | Corrected | Final Inspection | Quality control |  | Design prototype |  | Feature missing | Approved | Mistake of developer
| User New | user name: chỉ chấp nhận alphabet, số, gạch dưới | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [7 empty] | Delivered | Intergration test | Requirement |  | Detailed design |  | Other | Closed
| User New | Password: chỉ chấp nhận alphabet và số, không khoảng trắng | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [7 empty] | Error | Other Inspection | Test |  | Installation manual |  | Performance | Cofirmed
| User New | Confirm Password: chỉ chấp nhận alphabet và số, không khoảng trắng, và phải giống với password | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [7 empty] | Fixing | Other review |  |  | Meeting minute |  | Portablity | Cancelled
| User New | Email: nhập phải theo chuẩn email | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [7 empty] | Validated | Other test |  |  | Other |  | Security, Access control | Accepted
| User Edit | Password: chỉ chấp nhận alphabet và số, không khoảng trắng | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [8 empty] | Quality Inspection |  |  | Plan |  | Tools
| User Edit | Confirm Password: chỉ chấp nhận alphabet và số, không khoảng trắng, và phải giống với password | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [8 empty] | Regression test |  |  | Release note |  | User interface
| User Edit | Email: nhập phải theo chuẩn email | Error | Code review | Coding |  | Coding convention |  |  |  | TuTM | TuTM | [8 empty] | System test |  |  | Software module
[21 empty] | Unit test |  |  | System test case
System test plan
Test case
Test data
Test plan
Test report