## Task1-7
Project Code:
STT | Task | Resource | Duration | Status | Chất lượng hoàn thành | Khối Lượng hoàn thành | Thời gian hoàn thành | Thái độ làm việc | Ghi chú | Warning: This session is created only for doing value validation. Please do not do modify this.
1 | Complete SectionManager , CategoryManager , FrontPageManager , ActicleEdit forms | DungDV | 1 | Complete | 3 | 3 | 2 | 2 | Hoàn thành Form nhưng chưa bỏ vào Source3
2 | Complete ActicleManager, ActicleCopy , ActicleGlobalConfig form | DucNH | 1 | Complete | 3 | 3 | 2 | 2 | Hoàn thành Form nhưng chưa bỏ vào Source3 | Resource | Status | Quality
3 | Complete UserManager, NewMenuItem forms | KhoaVT | 1 | Complete | 3 | 3 | 3 | 3 |  | ThaoNX | Complete | 0
4 | Insert Toolboxs for Site Setting & System Setting form | HienTT | 1 | Complete | 3 | 3 | 3 | 3 |  | ThanhCV | InComplete | 1
5 | Insert actions for Toolboxs of Site Setting & System Setting form | HienTT | 2 | Complete | 3.5 | 4 | 3.5 | 3.5 |  | BaoDD |  | 1.5
6 | Study Zend_DB | LinhTA | 1 | InComplete | [5 empty] | TuanVA |  | 2
7 | Make a lab ( How to using Zend_DB ) and a demo | LinhTA | 2 | InComplete | [5 empty] | KhoaVT |  | 2.5
8 | Study Zend_Auth and make a LAB | DungDV | 1 | Complete | 3 | 3 | 2 | 2 |  | LinhTA |  | 3
9 | Make a lab : How to using Zend Decorartor with Zend Form | DucNH | 1 | Complete | 3 | 3.5 | 3 | 3 |  | TuTM |  | 3.5
10 | Make a Lab ( How to using Zend_Acl) | TuanVA | 2 | Complete | 3.5 | 3.5 | 3.5 | 3.5 |  | ThiVT |  | 4
11 | Design Admin template | BaoDD | 3 | Complete | 3.5 | 3.5 | 3.5 | 3.5 |  | HuyDV |  | 4.5
12 | Designe Front page template | HuyNV | 3 | Complete | 3.5 | 3.5 | 3.5 | 3.5 |  | HuyNV |  | 5
13 | Find all Filter & Vadilate in form and write it on DefectLog file | TuTM | 1 | Complete | 3.5 | 3 | 3.5 | 3.5 |  | HienTT
14 | Study Filter & Validate and make a simple LAB | TuTM | 2 | Complete | 3.5 | 3.5 | 3.5 | 3.5 |  | DungDV
15 | Insert Validate & Filter for form | TuTM | 1 | Complete | 2 | 3.5 | 3.5 | 3.5 |  | HuyNV
16 | Find all Filter & Vadilate in form and write it on DefectLog file | ThiVT | 1 | Complete | 3.5 | 3 | 3.5 | 3.5 |  | HienTT
17 | Study Filter & Validate and make a simple LAB | ThiVT | 2 | Complete | 3 | 3 | 3.5 | 3.5 |  | DungDV
18 | Insert Validate & Filter for form | ThiVT | 1 | Complete | 2 | 3.5 | 3.5 | 3.5
19 | Design Logic Diagram & Design DB | HuyDV | 3 | Complete | 2 | 2 | 3.5 | 3 | Thiếu nhiều Bảng
20 | Insert forms : ActicleManager, ActicleCopy, ActicleGlobalConfig, SectionManager, CategoryManager,FrontPageManager, ActicleEdit into Source3 | KhoaVT | 2 | InComplete |  |  |  |  | Trên Source3 chưa thấy đường dẫn tới form của DungDV