## Defect Log
Project Code: | CMS Click and Change
Created Date (*) | Title (*) | Description (*) | Status (*) | QC Activity | Defect Origin | Priority (*) | Product Type (*) | Severity (*) | Product (*) | Type | Detected By (*) | Assigned To (*) | Deadline (*) | Corrective Action (*) | Cause Analysis | Reason | Fixed Date (*) | Closed Date (*) | Warning: This session is created only for doing value validation. Please do not do modify this.
2011-10-21 | Media Option_Permission | Phân quyền Media cho user, dư thừa không cần thiết. | Error
2011-10-21 | Media Option_Component | Cấu hình media, dư thừa không cần thiết. | Error | [15 empty] | Member List | Status | QC Activity | Defect Origin | Priority | Product Type | Severity | Type | Status | Reason
2011-10-21 | Category và section | Lỗi giá trị không đồng nhất (giá trị liên kết giữa 2 bảng) | Error | [16 empty] | Accepted | Acceptance test | Coding | Immediately | Achitectural design | Fatal | Bussiness logic | Error | Change requirement
2011-10-21 | Article | Thiếu catid | Error | [16 empty] | Approved | After release review | Configuration Manament | High | CM Plan | Serious | Coding logic | Assigned | Duplicated
2011-10-21 | Event trong Article | Thiếu event select change của combox section | Error | [16 empty] | Assigned | After release test | Customer support | Normal | Coding convention | Medium | Coding standard | Fixing | No need to change
2011-10-21 | Media Manager | chkThumbnailView và chkDetailView không thể dùng checkbox | Error | [16 empty] | Cancelled | Audit | Deployment | Low | Customer saticfaction survey | Cosmetic | Data, Database integrity | Corrected | Other
2011-10-21 | Media Manager | txtFilePath bị dư | Error | [16 empty] | Closed | Code review | Design |  | Database |  | Design issue | Dilivered | Unable to fix
2011-10-21 | Media Manager | chkSelectFile không cần thiết | Error | [16 empty] | Cofirmed | Document review | Project Manament |  | Deployment package |  | Document | Validated | Unable to change
2011-10-21 | Media Manager | Thiếu sự kiện select chọn trong folder | Error | [16 empty] | Corrected | Final Inspection | Quality control |  | Design prototype |  | Feature missing | Approved | Mistake of developer
[20 empty] | Delivered | Intergration test | Requirement |  | Detailed design |  | Other | Closed
2011-10-21 | Language manager | Dư column Version | Error | [16 empty] | Error | Other Inspection | Test |  | Installation manual |  | Performance | Cofirmed
2011-10-21 | Language manager | Dư column Date | Error | [16 empty] | Fixing | Other review |  |  | Meeting minute |  | Portablity | Cancelled
2011-10-21 | New & Edit user | Dư phần Basic Setting | Error | [16 empty] | Validated | Other test |  |  | Other |  | Security, Access control | Accepted
2011-10-21 | New & Edit user | Dư các group user : publisher, editor, super administrator, author, editor. | Error | [17 empty] | Quality Inspection |  |  | Plan |  | Tools
2011-10-21 | New & Edit user(mapping items to db) | Dư column Cofirm password trong phần mapping to db | Error | [17 empty] | Regression test |  |  | Release note |  | User interface
2011-10-21 | new & edit user | Dùng các radion button thay cho cac check box trong Assigned User Groups | Error | [17 empty] | System test |  |  | Software module
2011-10-21 | Contend manager _ Article manager(Item Definition) | mô tả thiếu item btnhelp trong phần item definiton | Error | [17 empty] | Unit test |  |  | System test case
2011-10-21 | Contend manager_ Article manager(events) | Mô tả sai event của btnpublishArticle | Error | [20 empty] | System test plan
2011-10-21 | Contend manager_ Article manager(events) | Mô tả sai event của btnunpublishArticle | Error | [20 empty] | Test case
2011-10-21 | Contend manager_ Article manager(item definition) | các items : pageNumberList, itemNotes có type là : html, mô tả type của item chưa rõ.! | Error | [20 empty] | Test data
2011-10-21 | Contend manager_ Article manager(event) | Mô tả chưa chính xác event của btnreset | Error | [20 empty] | Test plan
|  |  | Error | [20 empty] | Test report
2011-10-21 | User Manage | database: dư Item Name checkbox" | Error
2011-10-21 | User Manage | database: dư Item Namen cboSelectGroup | Error
2011-10-21 | User Manage | database: dư Item Name cboSelectLogStatus | Error
2011-10-21 | MenuManager | database: dư Item Name colTitle | Error
2011-10-21 | MenuManager | database: dư Item Name colType | Error
2011-10-21 | MenuManager | database: dư Item Name col#publish | Error
2011-10-21 | MenuManager | database: dư Item Name col#unpublish | Error
2011-10-21 | MenuManager | database: dư Item Name colMenuItems | Error
Note on B4: Created Date: Ngày viết Log
Note on C4: Title: Tên Log
Note on D4: Description: Mô tả Log.
Note on E4: Status: Tình trạng của Log
Note on F4: QC Activity: Người viết Log phát hiện bug nhờ hành động nào.
Note on G4: Defect Origin: Bug xảy ra do bước nào trong quy trình phát triển
Note on H4: Priority: Tính cấp thiết của Bug (có phải sửa ngay hay không)
Note on I4: Product Type: Loại sản phẩm chứa Bug.
Note on J4: Serverity: Mức độ nghiêm trọng của Bug
Note on K4: Product: Sản phẩm chứa Bug. Lưu ý: ghi rõ file nào chứa bug, ở revision nào.
Note on L4: Type: Phân loại bug.
Note on M4: Detected By: Người phát hiện hoặc người viết Log.
Note on N4: Assigned To: Người được giao việc sửa lỗi.
Note on O4: DeadLine: Hạn chót phải sửa xong.
Note on P4: Corrective Action: Phải sửa lỗi như thế nào. Nếu có thể xảy ra những lỗi tương tự ở các file khác thì đề nghị sửa luôn ở đây.
Note on Q4: Cause Analysis: Nguyên nhân gây ra lỗi.
Note on R4: Reason: Loại nguyên nhân gây ra lỗi.
Note on S4: Fixed Date: Ngày sửa xong.
Note on T4: Closed Date: Ngày đóng Bug.